## Project schedule
| Egg Cracker | [5 empty] | Project start: | [7 empty] | 2025-08-25
| Senior Design 2 | Britney Hollie Misa Sheryl |  |  |  |  | Display week: | [7 empty] | 1
[7 empty] | 2025-08-25 | [6 empty] | 2025-09-01 | [6 empty] | 2025-09-08 | [6 empty] | 2025-09-15 | [6 empty] | 2025-09-22 | [6 empty] | 2025-09-29 | [6 empty] | 2025-10-06 | [6 empty] | 2025-10-13 | [6 empty] | 2025-10-20 | [6 empty] | 2025-10-27 | [6 empty] | 2025-11-03 | [6 empty] | 2025-11-10 | [6 empty] | 2025-11-17 | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01 | [6 empty] | 2025-12-08
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2025-08-25 to 2025-12-14
 | time axis 2025-08-25 to 2025-12-14
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
| Assignment Schedule |  | Paper Due | Assessment | Presentation |  | 2025-11-24: Fall Break
Equations
| Develop Design Equations |  | 0% | 2025-08-28 | 2025-09-25 | 29
| Create Force Diagrams for all Moving Parts |  | 0% | 2025-09-15 | 2025-09-29 | 15
| Determine Spring Constants and Measurements |  | 0% | 2025-09-29 | 2025-09-30 | 2
|  |  | 0% | 2025-09-30 | 2025-03-20 | -193
Design
| Disassemble Existing Device |  | 0% | 2025-08-25 | 2025-08-29 | 5
| Measure Componenets |  | 0% | 2025-08-29 | 2025-09-03 | 6
| Consider Initial Edits to Design |  | 0% | 2025-08-30 | 2025-09-15 | 17
| Develop Cost Analysis |  | 0% | 2025-09-15 | 2025-09-19 | 5
SolidWorks Simulation
| Complete Individual Parts CAD |  | 0% | 2025-08-29 | 2025-09-20 | 23
| Compile into Assembly |  | 0% | 2025-09-20 | 2025-09-27
| Ensure Assembly Functions through Simulation |  | 0% | 2025-09-27 | 2025-10-03
| Run Stress and Design Analysis |  | 0% | 2025-09-27 | 2025-10-03 | 7
Fabrication
| Print and Test Initial Prototype |  | 0% | 2025-08-25 | 2025-09-07 | 14
| Edit CAD with Updates |  | 0% | 2025-04-07 | 2025-04-13 | 7
| Print and Test Updates |  | 0% | 2025-04-14 | 2025-04-21 | 8
|  |  | 0% | 2025-04-24 | 2025-04-24 | 1
Insert new rows ABOVE this one | bar: 2025-08-25 to 2025-10-19
Formulas:
Display week: = [Display week:, row below]
Presentation = [Assessment]+28
Assessment = [Presentation, row above]
Assessment = [Presentation, row above]+1

## Tasks
Week | Date | Deliverable
1
2 | 2025-09-01 | Problem Statement | Writing Assignment
2 | 2025-09-07 | Design Criteria | Writing Assignment
3 | 2025-09-08 | Presentation 1 | Presentation
3 | 2025-09-10 | Peer Eval 1 | Evaluations
3 | 2025-09-14 | Potential Solutions | Writing Assignment
3 | 2025-09-19 | CAD | CAD
3 | 2025-09-20 | Send off to print | Printing
4 | 2025-09-21 | Preliminary Design | Writing Assignment
5 | 2025-09-22 | Presentation 2 | Presentation
5 | 2025-09-26 | Peer Eval 2 | Evaluations
5 | 2025-09-27 | CAD adjustments and reprint | CAD
5 | 2025-10-04 | CAD 3 and reprint | CAD
6 | 2025-10-05 | Chosen Intermediate Design | Writing Assignment
6 | 2025-10-05 | Advisor Check Off | Evaluations
7 | 2025-10-06 | Presentation 3 | Presentation
7 | 2025-10-10 | Peer Eval 3 | Evaluations
7 | 2025-10-10 | Self Assessment | Evaluations
7 | 2025-10-10 | Order Parts
7 | 2025-10-19 | Testing Methods
8
9
10
11 | 2025-11-09 | Progress Report 3
12 | 2025-11-16 | Preliminary Results
13 | 2025-11-20 | Presentation Day
14 | 2025-12-05 | Poster Presentation

## CAD
part | CAD
blade left | TRUE
blade right | TRUE
left handle | TRUE
right handle | TRUE
base lever | TRUE
body | TRUE
wedge | FALSE
egg holder | FALSE
egg separator | FALSE
center part | FALSE
assembly | FALSE